## Work List
TAG
1 |  | 2026-03-10 08:00 | 2026-03-13 20:00
2 |  | 2026-03-10 08:00 | 2026-03-13 20:00
3 |  | 2026-03-10 08:00 | 2026-03-13 20:00
4 |  | 2026-03-10 08:00 | 2026-03-13 20:00
5 |  | 2026-03-10 08:00 | 2026-03-13 20:00
6 |  | 2026-03-10 08:00 | 2026-03-13 20:00
7 |  | 2026-03-10 08:00 | 2026-03-13 20:00
8 |  | 2026-03-10 08:00 | 2026-03-13 20:00
9 |  | 2026-03-10 08:00 | 2026-03-13 20:00
10 |  | 2026-03-10 08:00 | 2026-03-13 20:00
11 |  | 2026-03-10 08:00 | 2026-03-13 20:00
12 |  | 2026-03-10 08:00 | 2026-03-13 20:00
13 |  | 2026-03-10 08:00 | 2026-03-13 20:00
14 |  | 2026-03-10 08:00 | 2026-03-13 20:00
15 |  | 2026-03-10 08:00 | 2026-03-13 20:00
16 |  | 2026-03-10 08:00 | 2026-03-13 20:00
17 |  | 2026-03-10 08:00 | 2026-03-13 20:00
18 |  | 2026-03-10 08:00 | 2026-03-13 20:00

## Sch.Plan
Item |  | Section | TAG | Description | % Complete | Duration | Start | Finish | Respon | MES Leader | PTW
| Work type |  |  | TPE_PP3_TA WORK NOV.2026 | 0% | 0 hrs | 2026-10-01 08:00 | 2026-11-30 10:00 |  |  |  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10 | [5 empty] | 11 | [5 empty] | 12 | [5 empty] | 13 | [5 empty] | 14 | [5 empty] | 15 | [5 empty] | 16 | [5 empty] | 17 | [5 empty] | 18 | [5 empty] | 19 | [5 empty] | 20 | [5 empty] | 21 | [5 empty] | 22 | [5 empty] | 23 | [5 empty] | 24 | [5 empty] | 25 | [5 empty] | 26 | [5 empty] | 27 | [5 empty] | 28 | [5 empty] | 29 | [5 empty] | 30
[12 empty] | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22 | 08-10 | 10-12 | 13-15 | 15-17 | 17-20 | 20-22
ME-CL-0001 | clean | 100 | D-3106A | TA26_D-3106A : PM 3Y HPWJ & Inspec CATL.Drum > ROI Support borescope | 100% | 14 Day | 2026-10-09 08:00 | 2026-11-22 20:00
|  |  |  | MER Disassembly Motor,Gear,Mechanical Seal | 0% | 0 hrs | 2026-10-10 08:00 | 2026-10-10 20:00
|  |  |  | Disassembly Pipe Line บนหัวถัง | 0% | 0 hrs | 2026-10-11 08:00 | 2026-10-12 20:00
|  |  |  | Disassembly Valve HV1307A [EE Support ถอดสาย] | 0% | 0 hrs | 2026-10-12 08:00 | 2026-11-13 20:00
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs | 2026-10-13 08:00 | 2026-10-20 20:00
|  |  |  | HPWJ Clening [ใช้หัว 3D] | 0% | 0 hrs | 2026-10-21 08:00 | 2026-10-25 20:00
|  |  |  | Air Blow | 0% | 0 hrs | 2026-10-26 08:00 | 2026-10-28 20:00
|  |  |  | Final Inspection By Bore Scope | 0% | 0 hrs | 2026-10-28 08:00 | 2026-11-02 20:00
|  |  |  | MER Install Mechanical Seal,Gear,Motor | 0% | 0 hrs | 2026-10-02 08:00 | 2026-11-15 20:00
|  |  |  | Install Pipe Line บนหัวถัง | 0% | 0 hrs
|  |  |  | Install Valve HV1307A [EE Support เข้าสาย] | 0% | 0 hrs
ME-CL-0002 | clean | 100 | D3106B | TA26_D-3106B : PM 3Y HPWJ & Inspec CATL.Drum > ROI Support borescope | 55% | 14 Day | 2026-10-09 08:00 | 2026-11-22 20:00
|  |  |  | MER Disassembly Motor,Gear,Mechanical Seal | 100% | 0 hrs
|  |  |  | Disassembly Pipe Line บนหัวถัง | 100% | 0 hrs
|  |  |  | Disassembly Valve HV1307B [EE Support ถอดสาย] | 100% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 100% | 0 hrs
|  |  |  | HPWJ Clening [ใช้หัว 3D] | 100% | 0 hrs
|  |  |  | Air Blow | 10% | 0 hrs
|  |  |  | Final Inspection By Bore Scope | 10% | 0 hrs
|  |  |  | MER Install Mechanical Seal,Gear,Motor | 10% | 0 hrs
|  |  |  | Install Pipe Line บนหัวถัง | 10% | 0 hrs
|  |  |  | Install Valve HV1307B [EE Support เข้าสาย] | 10% | 0 hrs
ME-CL-0003 | clean | 100 | Z3106A,B | TA26_Z-3106A/B : PM 1Y Water jet cleaning pot Vent D-3106A/B + inlet line from D-3106A/B | 0% | 12 Day | 2026-10-11 08:00 | 2026-11-22 20:00
|  |  |  | Disassembly Pipe Line บนหัวถัง 2" 6 Joint | 0% | 0 hrs
|  |  |  | Disassembly Pipe Line D3106A,B | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Install Pipe Line บนหัวถัง 2" 6 Joint | 0% | 0 hrs
|  |  |  | Install Pipe Line D3106A,B | 0% | 0 hrs
ME-CL-0004 | clean | 100 | D3103 | TA26_D-3103 : PM 1Y Water jet cleaning pot + line vent to ATM | 0% | 12 Day | 2026-10-11 08:00 | 2026-11-22 20:00
|  |  |  | Disassembly Pipe Line บนหัวถัง | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Install Pipe Line บนหัวถัง | 0% | 0 hrs
ME-CL-0005 | clean | 100 | D3108 | TA26_D-3108AB ->D-3201 : PM 1Y Water jet Cleaning Line MUD #100 | 0% | 13 Day | 2026-10-08 08:00 | 2026-11-22 20:00
|  |  |  | Disassembly Pipe Line | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Install Pipe Line | 0% | 0 hrs
ME-CL-0007 | Change line | 200 | R3201 | TA26_R-3200>R-3201 : PM 1Y Change line slurry 1" TK-Feed > "Recond" | 0% | 10 Day | 2026-11-11 08:00 | 2026-11-22 20:00
|  |  |  | Disassembly Pipe Line | 0% | 0 hrs
|  |  |  | Install Line [มี Spare เปลี่ยนรอประกอบหลังงาน Jet Line 8" R3200] | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Install Pipe Line | 0% | 0 hrs
ME-CL-0008 | clean | 200 | R3200 | TA26_R-3200 : PM 1Y Water jet Cleaning & Inspec borescope Loop line reactor 8" > ROI Support borescope | 0% | 10 Day | 2026-11-11 08:00 | 2026-11-22 20:00
|  |  |  | IE Disassembly สาย PV2201,PV….... | 0% | 0 hrs
|  |  |  | Disassembly Pipe Line | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Install Pipe Line | 0% | 0 hrs
|  |  |  | IE Install สาย PV2201,PV….... | 0% | 0 hrs
ME-CL-0012 | clean | 200 | Z3205A/B | TA26_Z-3205A/B : PM 1Y Water jet Cleaning & Inspec line sampling pot R-3201 + Clear powder loop line reactor R-3201 (ด้านล่าง) | 0% | 6 Day | 2026-11-14 08:00 | 2026-11-19 20:00
|  |  |  | Disassembly Pipe Line | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Install Pipe Line | 0% | 0 hrs
ME-CL-0013 | clean | 300 | D3304 | TA26_D-3304 : PM 3Y HPWJ Cleaning / Change demister | 0% | 10 Day | 2026-11-11 08:00 | 2026-11-22 20:00
|  |  |  | Loose Bolt Line,Disassembly Pipe Line [ใช้เครนยก Line] | 0% | 0 hrs
|  |  |  | Loose Bolt Cover ,Lifting Cover [ใช้เครนยก Cover] | 0% | 0 hrs
|  |  |  | Disassembly Demister | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening Vessel [รอ Confirm พี่วี clean แบบไหน] | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Install Demister | 0% | 0 hrs
|  |  |  | Lifting Install Cover [ใช้เครนยก Cover] | 0% | 0 hrs
|  |  |  | Lifting Install Line [ใช้เครนยก Line] | 0% | 0 hrs
ME-CL-0014 | clean | 300 | D3311 | TA26_D-3311 : PM 3Y HPWJ Cleaning / Change demister | 0% | 13 Day | 2026-11-12 08:00 | 2026-11-24 20:00
|  |  |  | Loose Bolt Line,Disassembly Pipe Line [ใช้เครนยก Line] | 0% | 0 hrs
|  |  |  | Loose Bolt Cover ,Lifting Cover [ใช้เครนยก Cover] | 0% | 0 hrs
|  |  |  | Disassembly Demister | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening Vessel [รอ Confirm พี่วี clean แบบไหน] | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Install Demister | 0% | 0 hrs
|  |  |  | Lifting Install Cover [ใช้เครนยก Cover] | 0% | 0 hrs
|  |  |  | Lifting Install Line [ใช้เครนยก Line] | 0% | 0 hrs
ME-CL-0015 | Weld | 300 | D3312 | TA26_D-3312 : PM 3Y HPWJ Cleaning / Change demister | 0% | 13 Day | 2026-11-12 08:00 | 2026-11-24 20:00
|  |  |  | Loose Bolt Line,Disassembly Pipe Line [ใช้เครนยก Line] | 0% | 0 hrs
|  |  |  | Loose Bolt Cover ,Lifting Cover [ใช้เครนยก Cover] | 0% | 0 hrs
|  |  |  | Disassembly Demister | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening Vessel [รอ Confirm พี่วี clean แบบไหน] | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Install Demister | 0% | 0 hrs
|  |  |  | Lifting Install Cover [ใช้เครนยก Cover] | 0% | 0 hrs
|  |  |  | Lifting Install Line [ใช้เครนยก Line] | 0% | 0 hrs
ME-CL-0016 | Cutting | 300 | E3303 | TA26__E-3303"C" : PM 1Y Drop & HPWJ Exchanger propylene scrubber > Liftting "chain hoist" ใช้งานตัวเดิม | 0% | 14 Day | 2026-11-10 08:00 | 2026-11-23 20:00
ME-CL-0022 | Confine | 300 | T3301 | TA26_T-3301 : PM 3Y Cleaning & Inspec tray 23 Set > Confine (ROI Check) | 0% | 12 Day | 2026-11-12 08:00 | 2026-11-23 20:00
|  |  |  | Loose Bolt , Open Manhold | 0% | 0 hrs
|  |  |  | Disassembly Valve FV3205 [ IE Support ถอดสาย] | 0% | 0 hrs
|  |  |  | Loose Bolt Flange 34" 300 fb , Drop Buttom Cover | 0% | 0 hrs
|  |  |  | Loose Bolt Flange 34" 300 fb , Drop Exchanger | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | Cleaning | 0% | 0 hrs
|  |  |  | Inspec tray 23 Set [Confine ROI Check] | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection , ROI Support Borescope | 0% | 0 hrs
|  |  |  | Close Monhold , Torque Bolt | 0% | 0 hrs
|  |  |  | Install Exchanger , Torque Bolt | 0% | 0 hrs
|  |  |  | Install Cover , Torque Bolt | 0% | 0 hrs
|  |  |  | Install Valve FV3205 [ IE Support เข้าสาย] | 0% | 0 hrs
ME-CL-0017 | Change line | 300 | T3301 | TA26_PM 1Y HPWJ Cleaning line 1" SL-30014 (100 m.) under E-3303 (ใส้ไก่) > ROI Support Borescope | 0% | 13 Day | 2026-11-11 08:00 | 2026-11-23 20:00
| clean |  |  | Disassembly Line Pipe | 0% | 0 hrs
| clean |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
| clean |  |  | HPWJ Clening | 0% | 0 hrs
| clean |  |  | Air Blow | 0% | 0 hrs
| Weld |  |  | Final Inspection , ROI Support Borescope | 0% | 0 hrs
| Cutting |  |  | Install Line Pipe | 0% | 0 hrs
Confine
ME-CL-0018 |  | 300 | F3301 | TA26_F-3301: PM 1Y Insert Blind & De-Blind Isolate support OPE ( 02/11/2026_09:00 น. กลับ Blind Isolate loop) | 0% | 2 Day | 2026-11-02 08:00 | 2026-11-21 20:00
|  |  |  | Disassembly Line 12" สลับ Blind | 0% | 2 hrs | 2026-11-02 08:00 | 2026-11-02 20:00
|  |  |  | สลับ Blind กลับ Line 12" | 0% | 2 hrs | 2026-11-21 08:00 | 2026-11-21 20:00
0%
ME-CL-0020 |  | 300 | E3304 | TA26_E-3304 > T-3302 : PM 3Y Water jet cleanning > ROI Support Borescope | 0% | 12 Day | 2026-11-13 08:00 | 2026-11-23 20:00
ME-CL-0023 |  | 300 | T3302 | TA26_T-3302 : PM 3Y Cleaning & Inspec tray 21 Set > Confine (ROI Check) | 0% | 12 Day | 2026-11-12 08:00 | 2026-11-23 20:00
|  |  |  | Loose Bolt & Open Manhold 3 ฝา | 0% | 0 hrs
|  |  |  | Loose Bolt Cover ,Lifting Cover [ใช้เครนยก Cover] | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening [ Exchanger] | 0% | 0 hrs
|  |  |  | Set Up For Cleaning & Inspec tray 21 Set | 0% | 0 hrs
|  |  |  | HPWJ Clening [ Exchanger]งานทำคู่ขนานงาน Cleaning & Inspec tray | 0% | 0 hrs
|  |  |  | Cleaning & Inspec tray 21 Set | 0% | 0 hrs
|  |  |  | Air Blow Tube Exchanger | 0% | 0 hrs
|  |  |  | Final Inspection , ROI Support Borescope | 0% | 0 hrs
|  |  |  | Lifting Cover [ใช้เครนยก Cover] , Torque Bolt Cover | 0% | 0 hrs
|  |  |  | Inspect OPE , MES Close Manhold ฝาบน | 0% | 0 hrs
|  |  |  | Inspect OPE , MES Close Manhold ฝากลาง | 0% | 0 hrs
|  |  |  | Inspect OPE , MES Close Manhold ฝาล่าง | 0% | 0 hrs
ME-CL-0021 |  | 300 | E3305 | TA26_E-3305 : PM 3Y Water jet cleanning > ROI Support Borescope | 0% | 12 Day | 2026-11-12 08:00 | 2026-11-23 20:00
|  |  |  | Disassembly Pipe Line | 0% | 0 hrs
|  |  |  | Disassembly Cover | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection , ROI Support Borescope | 0% | 0 hrs
|  |  |  | Install Cover | 0% | 0 hrs
|  |  |  | Install Pipe Line | 0% | 0 hrs
ME-CL-0024 |  | 300 | Z3302A,B | TA26_Z-3302A/B : PM 1Y Water jet Cleaning & Inspec line sampling pot D-3301 + Clear powder loop line reactor R-3202 (ด้านล่าง) | 0% | 13 Day | 2026-11-10 08:00 | 2026-11-23 20:00
|  |  |  | Disassembly Pipe Line Z3302A,B | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening | 0% | 0 hrs
|  |  |  | Inspec line sampling pot D-3301 | 0% | 0 hrs
|  |  |  | Clear powder loop line reactor R-3202 (ด้านล่าง) | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Install Pipe Line Z3302A,B | 0% | 0 hrs
|  |  |  | Install line sampling pot D-3301 | 0% | 0 hrs
|  |  |  | Install loop line reactor R-3202 (ด้านล่าง) | 0% | 0 hrs
ME-CL-0026 |  | 400 | E3401A | TA26_E-3401A : PM 3Y Water jet cleaning "CIRCULATION GAS COOLER A" ( Crane 130 T. ) > Critical work + High risk | 0% | 14 Day | 2026-11-12 08:00 | 2026-11-23 20:00
ME-CL-0027 |  | 400 | E3401B | TA26_E-3401B : PM 3Y Water jet cleaning "CIRCULATION GAS COOLER A" ( Crane 130 T. ) > Critical work + High risk | 0% | 14 Day | 2026-11-09 08:00 | 2026-11-23 20:00
|  |  |  | Loose Bolt Line , Cover E3401A,B [อัลฟ่า] | 0% | 0 hrs | 2026-11-08 08:00 | 2026-11-08 22:00
|  |  |  | Lifting Line 32" ตัว R [ใช้เครนยก 130 Ton] ทีม Project มี Modify Line ต้องเอา Marker ขึ้นด้านบน | 0% | 0 hrs | 2026-11-09 08:00 | 2026-11-09 10:00
|  |  |  | Modify นั่งร้านเพื่อยก Top Cover | 0% | 0 hrs | 2026-11-09 10:00 | 2026-11-09 12:00
|  |  |  | Lifting Top Cover E3401A [ใช้เครนยก 130 Ton] [Weight Top Cover 5 Ton] | 0% | 0 hrs | 2026-11-09 12:00 | 2026-11-09 14:00
|  |  |  | Lifting Line ตัว S 40" [ใช้เครนยก 130 Ton] | 0% | 0 hrs | 2026-11-09 14:00 | 2026-11-09 16:00
|  |  |  | Lifting Top Cover E3401B [ใช้เครนยก 130 Ton] | 0% | 0 hrs | 2026-11-09 16:00 | 2026-11-09 18:00
|  |  |  | Drop Line Elbow 32" ใต้ E3401B | 0% | 0 hrs | 2026-11-09 17:00 | 2026-11-09 20:00
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs | 2026-11-09 20:00 | 2026-11-09 22:00
|  |  |  | HPWJ Clening Exchanger,Line Pipe | 0% | 0 hrs | 2026-11-10 08:00 | 2026-11-13 13:00
|  |  |  | Air Blow | 0% | 0 hrs | 2026-11-13 13:00 | 2026-11-13 22:00
|  |  |  | Final Inspection [PDM ส่องกล้อง] | 0% | 0 hrs | 2026-11-14 08:00 | 2026-11-14 22:00
|  |  |  | Install Top Cover E3401B [ใช้เครนยก 130 Ton] | 0% | 0 hrs | 2026-11-15 08:00 | 2026-11-15 10:00
|  |  |  | Install Line ตัว S 40" [ใช้เครนยก 130 Ton] | 0% | 0 hrs | 2026-11-15 10:00 | 2026-11-15 12:00
|  |  |  | Install Top Cover E3401A [ใช้เครนยก 130 Ton] | 0% | 0 hrs | 2026-11-15 12:00 | 2026-11-15 14:00
|  |  |  | Install Line 32" [ใช้เครนยก 130 Ton] | 0% | 0 hrs | 2026-11-15 14:00 | 2026-11-15 16:00
|  |  |  | Install Line Elbow 32" ใต้ E3401B | 0% | 0 hrs | 2026-11-15 16:00 | 2026-11-15 18:00
|  |  |  | Torque Bolt Line , Cover E3401A,B [อัลฟ่า] | 0% | 0 hrs | 2026-11-15 18:00 | 2026-11-15 22:00
ME-CL-0028 |  | 400 | C3401 | TA26_C-3401 > R-3401 : PM 3Y Remove line disc."เขาควาย" Water jet Cleaning & Inspec ( Crane 70 T. ) | 0% | 13 Day | 2026-11-10 08:00 | 2026-11-23 20:00
|  |  |  | Loose Bolt Line disc."เขาควาย" [อัลฟ่า] | 0% | 0 hrs | 2026-11-08 08:00 | 2026-11-08 22:00
|  |  |  | Lifting Remove line disc."เขาควาย" [ใช้เครนยก 70 Ton] | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening Exchanger,Line Pipe | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Lifting Install line disc."เขาควาย" [ใช้เครนยก 70 Ton] | 0% | 0 hrs
|  |  |  | Torque Bolt Line disc."เขาควาย" [อัลฟ่า] | 0% | 0 hrs
ME-CL-0029 |  | 400 | R3401 | TA26_R-3401 : PM 1Y Open manhold Manual Cleaning TOP & BOTTOM grid > Manual _Confine _ ( 07/09/2026 Open Manhold_13:00 น.) | 0% |  | 2026-11-07 13:00 | 2026-11-23 20:00
|  |  |  | Open Manhold 3 ฝา | 0% | 0 hrs | 2026-11-07 13:00 | 2026-11-07 20:00
|  |  |  | TSP เตรียมระบบระบายอากาศ |  |  | 2026-11-07 13:00 | 2026-11-07 20:00
|  |  |  | Manule Clean Grid [Confine] | 0% | 0 hrs | 2026-11-10 08:00 | 2026-11-23 20:00
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Close Manhold 3 ฝา | 0% | 0 hrs
ME-CL-0030 |  | 400 | R3401 > T3301 | TA26_R-3401 : PM 1Y Water jet Cleaning & Inspec line Pot PD ทางลง Common Z-3401A/B --> Line 8" F-3301 > ROI Support Borescope | 0% | 13 Day | 2026-11-11 08:00 | 2026-11-23 20:00
|  |  |  | Disassembly Pipe Line Z3401A,B | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening Line Pipe | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection , ROI Support Borescope | 0% | 0 hrs
|  |  |  | Install Pipe Line Z3401A,B | 0% | 0 hrs |  |  | - | -
ME-CL-0031 |  | 400 | R3401 | TA26_Z-3401A/B : PM 1Y Water jet cleaning Line Balance loop R-3401> ROI Support Borescope | 0% | 13 Day | 2026-11-11 08:00 | 2026-11-23 20:00
|  |  |  | Disassembly Pipe Line | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening Line Pipe | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Final Inspection , ROI Support Borescope | 0% | 0 hrs
|  |  |  | Install Pipe Line | 0% | 0 hrs
ME-CL-0032 |  | 400 | E3402 | TA26_E-3402 : PM 3Y Change Exchanger "NEW" Complete set | 0% | 12 Day | 2026-11-12 08:00 | 2026-11-23 20:00
|  |  |  | Disassembly Pipe Line | 0% | 0 hrs
|  |  |  | Remove Exchanger | 0% | 0 hrs
|  |  |  | Install Exchanger [ตัว Spare] | 0% | 0 hrs
|  |  |  | Install Pipe Line | 0% | 0 hrs
ME-CL-0033 |  | 400 | E3404 | TA26_E-3404 : PM 3Y Water jet Cleaning & Coating tube sheet | 0% | 12 Day | 2026-11-12 08:00 | 2026-11-23 20:00
|  |  |  | Disassembly Pipe Line | 0% | 0 hrs
|  |  |  | Remove Exchanger [To Work Shop] | 0% | 0 hrs
|  |  |  | TSP รับของออกไป water Jet ที่ TSP | 0% | 0 hrs
|  |  |  | บ. ENECON รับไป Coating หน้า Tube sheet | 0% | 0 hrs
|  |  |  | Install Tube [ TSP] | 0% | 0 hrs
|  |  |  | Hydrostatic Test Sheel [ใช้ น้ำมัน Test ] | 0% | 0 hrs
|  |  |  | Hydrostatic Test Sheel [ใช้น้ำ Test ] | 0% | 0 hrs
|  |  |  | Install Exchanger On-Site | 0% | 0 hrs
ME-CL-0034 |  | 500 | D3501 | TA26_D-3501 : PM 1Y Water jet Cleaning inside drum + Inspec sparging ring > Confine ( เปิด Manhold 07/11/2026 18:00 น.) | 0% |  | 2026-11-07 13:00 | 2026-11-23 20:00
|  |  |  | Open Manhold | 0% | 0 hrs | 2026-11-07 18:00 | 2026-11-07 20:00
|  |  |  | TSP เตรียมระบบระบายอากาศ |  |  | 2026-11-07 18:00 | 2026-11-07 20:00
|  |  |  | Disassembly Pipe Line Buttom | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening inside drum [3D] | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | ROI Install Scaffolding [ Confine ROI เปิด Work ] | 0% | 0 hrs
|  |  |  | ROI Inspec sparging ring [ Confine ROI เปิด Work ] | 0% | 0 hrs
|  |  |  | ROI Remove Scaffolding [ Confine ROI เปิด Work ] | 0% | 0 hrs
|  |  |  | HPWJ Clening inside drum [3D] รอถามพี่ทวี ว่าต้อง Clean หลังจาก Inspect แล้วรึเปล่า | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Close Manhold | 0% | 0 hrs
|  |  |  | Install Pipe Line Buttom | 0% | 0 hrs
ME-CL-0035 |  | 500 | 10PP3-D3502 | TA26_D-3502 : PM 1Y Water jet Cleaning inside dryer + Inspec plate patition > Confine ( เปิด Manhold 07/11/2026 18:00 น.) | 0% |  | 2026-11-07 13:00 | 2026-11-23 20:00
|  |  |  | Open Manhold | 0% | 0 hrs | 2026-11-07 18:00 | 2026-11-07 20:00
|  |  |  | Disassembly Pipe Line Buttom | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening inside drum [3D] | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | ROI Install Scaffolding [ Confine ROI เปิด Work ] | 0% | 0 hrs
|  |  |  | ROI Inspec sparging ring [ Confine ROI เปิด Work ] | 0% | 0 hrs
|  |  |  | ROI Remove Scaffolding [ Confine ROI เปิด Work ] | 0% | 0 hrs
|  |  |  | HPWJ Clening inside drum [3D] รอถามพี่ทวี ว่าต้อง Clean หลังจาก Inspect แล้วรึเปล่า | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Close Manhold | 0% | 0 hrs
|  |  |  | Install Pipe Line Buttom | 0% | 0 hrs
ME-CL-0036 |  | 500 | 10PP3-D3506 | TA26_D-3506+line balance > F-3502 : PM 1Y Water jet Cleaning & Inspec hopper | 0% | 10 Day | 2026-11-13 08:00 | 2026-11-22 20:00
|  |  |  | Disassembly Pipe Line | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening | 0% | 0 hrs
|  |  |  | HPWJ Clening Pipe | 0% | 0 hrs
|  |  |  | HPWJ Clening Inside Hopper | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Install Pipe Line | 0% | 0 hrs
ME-CL-0037 |  | 500 | E3501 | TA26_E-3501 > T-3501 : PM 3Y Water jet cleanning | 0% | 10 Day | 2026-11-13 08:00 | 2026-11-22 20:00
ME-CL-0038 |  | 500 | T3501 | TA26_T-3501 : PM 3Y Cleaning & Inspec tray 15 set > Confine (ROI Check) | 0% | 10 Day | 2026-11-13 08:00 | 2026-11-22 20:00
|  |  |  | Disassembly Pipe Line Top Cover | 0% | 0 hrs
|  |  |  | Disassembly Pipe Line Buttom | 0% | 0 hrs
|  |  |  | Lifting Remove Top Cover E3501 [ใช้เครนยก 130 Ton] | 0% | 0 hrs
|  |  |  | Lifting Remove Exchanger E3501 [ใช้เครนยก 130 Ton] | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening [ Exchanger] | 0% | 0 hrs
|  |  |  | Set Up For Cleaning & Inspec tray 15 Set | 0% | 0 hrs
|  |  |  | HPWJ Clening [ Exchanger]งานทำคู่ขนานงาน Cleaning & Inspec tray | 0% | 0 hrs
|  |  |  | Cleaning & Inspec tray 15 Set | 0% | 0 hrs
|  |  |  | Air Blow Tube Exchanger | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Lifting Install Exchanger E3501 [ใช้เครนยก 130 Ton] | 0% | 0 hrs
|  |  |  | Lifting Install Top Cover E3501 [ใช้เครนยก 130 Ton] | 0% | 0 hrs
|  |  |  | Install Pipe Line Top Cover | 0% | 0 hrs
|  |  |  | Install Pipe Line Buttom | 0% | 0 hrs
ME-CL-0039 |  | 500 |  | TA26_T-3502 : PM 3Y Cleaning & Inspec tray 8 set > Confine (ROI Check) / Clean Or Change demister | 0% | 10 Day | 2026-11-13 08:00 | 2026-11-22 20:00
ME-CL-0040 |  | 500 |  | TA26_E-3506 : PM 3Y Water jet cleanning > ROI Support Borescope | 0% | 9 Day | 2026-11-14 08:00 | 2026-11-22 20:00
|  |  |  | Disassembly Pipe Line Top Cover | 0% | 0 hrs
|  |  |  | Disassembly Pipe Line Buttom | 0% | 0 hrs
|  |  |  | Lifting Remove Top Cover T3502 [ใช้เครนยก 130 Ton] | 0% | 0 hrs
|  |  |  | Lifting Remove Exchanger E3502 [ใช้เครนยก 130 Ton] | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening [ Exchanger] | 0% | 0 hrs
|  |  |  | Set Up For Cleaning & Inspec tray 8 Set | 0% | 0 hrs
|  |  |  | HPWJ Clening [ Exchanger]งานทำคู่ขนานงาน Cleaning & Inspec tray | 0% | 0 hrs
|  |  |  | Cleaning & Inspec tray 8 Set | 0% | 0 hrs
|  |  |  | Air Blow Tube Exchanger | 0% | 0 hrs
|  |  |  | Final Inspection | 0% | 0 hrs
|  |  |  | Lifting Install Exchanger T3502 [ใช้เครนยก 130 Ton] | 0% | 0 hrs
|  |  |  | Lifting Install Top Cover E3502 [ใช้เครนยก 130 Ton] | 0% | 0 hrs
|  |  |  | Install Pipe Line Top Cover | 0% | 0 hrs
|  |  |  | Install Pipe Line Buttom | 0% | 0 hrs
ME-CL-0041 |  | 500 | E3503 | TA26_E-3503 : PM 1Y Water jet Cleaning nitrogen heater "Fin Plate" | 0% | 9 Day | 2026-11-14 08:00 | 2026-11-22 20:00
|  |  |  | Disassembly Pipe Line Suction , Dischrage | 0% | 0 hrs
|  |  |  | Disassembly Pipe Line Steam Inlet,Outlet | 0% | 0 hrs
|  |  |  | Loose Bolt Casing Flange 4 Set | 0% | 0 hrs
|  |  |  | Remove Fin Tube 4 Set | 0% | 0 hrs
|  |  |  | Set Up For HPWJ Clening [ Exchanger] ถามพี่วี วิธีการ Clean | 0% | 0 hrs
|  |  |  | HPWJ Clening | 0% | 0 hrs
|  |  |  | After Clean inspection | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Install Fin Tube 4 Set | 0% | 0 hrs
|  |  |  | Tor Bolt Casing Flange 4 Set | 0% | 0 hrs
0%
ME-CL-0042 |  | 500 | 10PP3-S3501 > T3501 | TA26_S-3501 : PM 1Y Water jet Cleaning & Inspec Cyclone + Line 12" > T-3501 | 0% | 10 Day | 2026-11-12 08:00 | 2026-11-22 20:00
|  |  |  | Disassembly Pipe Line Suction 12" | 0% | 0 hrs
|  |  |  | Disassembly Valve 12" | 0% | 0 hrs
|  |  |  | Disassembly Pipe Line Discharge 12" | 0% | 0 hrs
|  |  |  | Set Up For HPWJ | 0% | 0 hrs
|  |  |  | HPWJ Clening Line 12" | 0% | 0 hrs
|  |  |  | After Clean inspection | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | Install Pipe Line Suction 12" | 0% | 0 hrs
|  |  |  | Install Valve 12" | 0% | 0 hrs
|  |  |  | Install Pipe Line Discharge 12" | 0% | 0 hrs
0%
ME-CL-0043 |  | 500 | 10PP3-S3502 > T3502 | TA26_S-3502 : PM 1Y Water jet Cleaning & Line Cyclone 22" > T-3502 | 0% | 10 Day | 2026-11-12 08:00 | 2026-11-22 20:00
|  |  |  | Disassembly Pipe Line Suction 22" | 0% | 0 hrs
|  |  |  | Disassembly Pipe Line Discharge 22" | 0% | 0 hrs
|  |  |  | Set Up For HPWJ | 0% | 0 hrs
|  |  |  | HPWJ Clening Line 22" | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | After Clean inspection | 0% | 0 hrs
|  |  |  | Install Pipe Line Suction 22" | 0% | 0 hrs
|  |  |  | Install Pipe Line Discharge 22" | 0% | 0 hrs
0%
ME-CL-0044 |  | 600 | 10PP3-D3601 | TA26_D-3601 : PM 3Y Isolate Blind line Flare 26" (08/11/2026_10:00 น. กลับ Blind) ( กลับ Blind คืน loop 30/11/2026) | 0% | 2 Day | 2026-11-08 13:00 | 2026-11-30 20:00
|  |  |  | Isolate Blind line Flare 26"[ก่อนถอด Blind ต้องใช้ผ้าใบแบบหนาไม่มีรอยรั่วเพื่อป้องกันน้ำมันไหลออกจากท่อ] | 0% | 0 hrs | 2026-11-08 10:00 | 2026-11-07 20:00
|  |  |  | Install Blind line Flare 26" | 0% | 0 hrs | 2026-11-30 08:00 | 2026-11-30 16:00
0%
ME-CL-0045 |  | 600 | 10PP3-D3601 | TA26_D-3601 : PM 3Y Clear powder > Water jet cleaning Inside drum | 0% | 7 Day | 2026-11-15 13:00 | 2026-11-21 20:00
|  |  |  | Open บน Manhold 20" | 0% | 0 hrs
|  |  |  | Open กลาง Manhold 20" | 0% | 0 hrs
|  |  |  | Disassembly Pipe Line Suction 4" | 0% | 0 hrs
|  |  |  | Drain Powder [ Powder ที่ค้างภายในถัง] | 0% | 0 hrs
|  |  |  | Disassembly Control Valve 4" [ IE support ถอดสานไฟ] | 0% | 0 hrs
|  |  |  | Disassembly Flange 20", Flange 4" | 0% | 0 hrs
|  |  |  | Set Up For HPWJ | 0% | 0 hrs
|  |  |  | HPWJ Clening Line Inside Drum | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | After Clean inspection | 0% | 0 hrs
|  |  |  | Close Manhold 20" [บน] | 0% | 0 hrs
|  |  |  | Close Manhold 20" [กลาง] | 0% | 0 hrs
|  |  |  | Install Flange 20", Flange,Line Pipe 4" | 0% | 0 hrs
|  |  |  | Install Control Valve 4" [ IE support เข้าสายไฟ] | 0% | 0 hrs
0%
ME-CL-0046 |  | 600 | 10PP3-D3602 | TA26_D-3602 : PM 3Y Clear powder > Water jet cleaning Inside drum | 0% | 7 Day | 2026-11-15 13:00 | 2026-11-21 20:00
|  |  |  | Disassembly Pipe 4" | 0% | 0 hrs
|  |  |  | Open กลาง Manhold 20" | 0% | 0 hrs
|  |  |  | Disassembly Pipe Line Suction 4" | 0% | 0 hrs
|  |  |  | Drain Powder [ Powder ที่ค้างภายในถัง] | 0% | 0 hrs
|  |  |  | Disassembly Control Valve 4" [ IE support ถอดสายไฟ] | 0% | 0 hrs
|  |  |  | Disassembly Flange 20", Flange 4" | 0% | 0 hrs
|  |  |  | Set Up For HPWJ | 0% | 0 hrs
|  |  |  | HPWJ Clening Line Inside Drum | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | After Clean inspection | 0% | 0 hrs
|  |  |  | Install Pipe 4" | 0% | 0 hrs
|  |  |  | Close Manhold 20" [กลาง] | 0% | 0 hrs
|  |  |  | Install Flange 20", Flange,Line Pipe 4" | 0% | 0 hrs
|  |  |  | Install Control Valve 4" [ IE support เข้าสายไฟ] | 0% | 0 hrs
0%
ME-CL-0047 |  | 600 | 10PP3-D3603 | TA26_D-3603 : PM 3Y Clear powder > Water jet cleaning Inside drum | 0% | 7 Day | 2026-11-15 13:00 | 2026-11-21 20:00
|  |  |  | Disassembly Pipe 4" | 0% | 0 hrs
|  |  |  | Open กลาง Manhold 20" | 0% | 0 hrs
|  |  |  | Disassembly Pipe Line Suction 4" | 0% | 0 hrs
|  |  |  | Drain Powder [ Powder ที่ค้างภายในถัง] | 0% | 0 hrs
|  |  |  | Disassembly Control Valve 4" [ IE support ถอดสายไฟ] | 0% | 0 hrs
|  |  |  | Disassembly Flange 20", Flange 4" | 0% | 0 hrs
|  |  |  | Set Up For HPWJ | 0% | 0 hrs
|  |  |  | HPWJ Clening Line Inside Drum | 0% | 0 hrs
|  |  |  | Air Blow | 0% | 0 hrs
|  |  |  | After Clean inspection | 0% | 0 hrs
|  |  |  | Install Pipe 4" | 0% | 0 hrs
|  |  |  | Close Manhold 20" [กลาง] | 0% | 0 hrs
|  |  |  | Install Flange 20", Flange,Line Pipe 4" | 0% | 0 hrs
|  |  |  | Install Control Valve 4" [ IE support เข้าสายไฟ] | 0% | 0 hrs
|  | 800 |  | Disassembly Flex Z3857 12" TO TK-3804 3 Joint
Disassembly Flex 4" TK-3804 TO F3824 3 Joint
Open Manhold TK-3804 20" 1 Joint
Disassembly Flex 4" TK-3804 TO W3804 7 Joint
Disassembly Flex 10" TK-3804 TO W3804 3 Joint
Disassembly Flex 8" W3804 TO M3803 4 Joint
Water Jet Inside Drum & Pipe Line TK3804
Disassembly Flex 3" TK-3806 To F3825 5 Joint
Disassembly Flex 8" TK-3806 To Z3868 3 Joint
Disassembly Flex 3" TK-3806 To W3806 3 Joint
Water Jet Inside Drum & Pipe Line TK3806
Disassembly Flex 8" W3806 To M3803 3 Joint
ME-PM-0060 | ศิริพงษ์ |  |  | TA26_P-3671C : PM 6Y O/H PUMP COOLING > 5 Tons (เข้าก่อน) > "Lifting > 5T ( 8,157 KG)" |  |  | 2026-11-06 08:00 | 2026-11-25 08:00
Check Alignment ก่อนถอด Pump
Disassembly Line Suction & Discharge Pump
Disassembly Coupling Pump
Lifting Pump [ใช้เครนยก 130 Ton] "Lifting > 5T ( 8,157 KG)"
Overhaul Pump [Work Shop PSS]
Lifting Pump Install [ใช้เครนยก 130 Ton] "Lifting > 5T ( 8,157 KG)"
Install Coupling Pump Motor
Alignment Pump Motor
Install Line Suction & Discharge Pump
Test Leak Line Suction & Discharge Pump
Test Run Pump[ PDM Support Ckeck Vibration]
ME-PM-0017 | ศิริพงษ์ |  |  | TA26_C-3671A : PM 6Y O/H Gear cooling "Change complete set gear" > Confine (Gear=1,250 kg/Blade coupling = 1,529 kg รวม 2,779 KG.) |  |  | 2026-11-08 08:00 | 2026-11-21 08:00
|  |  |  | งานตั้งนั่งร้าน [Confine] |  |  | 2026-11-08 08:00 | 2026-11-08 20:00
|  |  |  | Check Alignment ก่อนถอด Motor&Gear |  |  | 2026-11-09 08:00
Check องศาใบก่อนถอด
Drain Oil Gear [ก่อน Drain ตรวจสอบ Line น้ำมันก่อนถอดว่ามีจุดรั่วรึเปล่า]
Disassembly Coupling Gear & Motor
Disassembly Line Lube Oil Gear
Loose Bolt Gear
Lifting Gear&Blade [ใช้เครนยก 130 Ton] (Gear=1,250 kg/Blade coupling = 1,529 kg รวม 2,779 KG.)
Disassembly Blade Coupling
Install Blade Coupling [New Gear]
Lifting Gear&Blade Install [ใช้เครนยก 130 Ton] (Gear=1,250 kg/Blade coupling = 1,529 kg รวม 2,779 KG.)
Torque Bolt Gear
Install Coupling Gear & Motor [ Check ระยะ Coupling ก่อนประกอบตาม Check Sheet]
Alignment Motor&Gear
ปรับองศาใบ[ตาม Check Sheet]
Install Line Lube Oil Gear
Fill Up Lube Oil Gear[เช็ค Leak Oil ตามจุดต่อทุกจุด]
Test Run [ PDM Support Ckeck Vibration]
ตรวจสอบระดับน้ำมันขณะ Test Run เป็นอย่างแรก
ME-CL-0050 | ศิริพงษ์ |  |  | TA26_Z-3671A,B,C PM 3Y Cleanning ดูด sludge ในบ่อ Cooling + Change Nozzle > Confine |  |  | 2026-11-11 08:00 | 2026-11-21 20:00
Change Spary Nozzel Z3671A,B,C
OPE Drain Water Sum Screen Cooling Z3671A,B,C
TSP Water Jet Sum Screen Cooling Z3671A,B,C
TSP ดูดน้ำ Sum Screen Cooling Z3671A,B,C
TSP Change filter + Clean บ่อพัก LC ก่อนเข้า CW
ME-CL-0049 | ศิริพงษ์ |  |  | TA26_Z-3671A,B,C PM 3Y Change filter + Clean บ่อพัก LC ก่อนเข้า CW |  |  | 2026-11-11 08:00 | 2026-11-21 20:00
Water Jet & Clean บ่อพัก LC ก่อนเข้า CW
ME-CL-0077 | ศุภชัย |  |  | TA26_Z-3901A : PM 1Y Water jet cleaning inside SSB Drum Blender > Additive building > Confine |  |  | 2026-11-03 09:00 | 2026-11-07 23:00
ขนอุปกรณ์
|  |  |  | Open Top Cover T3902A,B,C |  |  | 2026-11-03 09:00 | 2026-11-03 12:00
|  |  |  | Remove Line Pipe Outlet T3902 A,B,C |  |  | 2026-11-03 12:00 | 2026-11-03 15:00
|  |  |  | Open Top Cover Z3901A,B,C |  |  | 2026-11-03 15:00 | 2026-11-03 17:00
|  |  |  | Disassembly Line Outlet Z3901A,B,C |  |  | 2026-11-03 17:00 | 2026-11-03 19:00
|  |  |  | Set Up For HPWJ |  |  | 2026-11-03 19:00 | 2026-11-03 22:00
|  |  |  | HPWJ Clening Line Inside T3902A,B,C |  |  | 2026-11-04 08:00 | 2026-11-05 22:00
|  |  |  | HPWJ Clening Line Inside Drum Z3901A,B,C [Confine] |  |  | 2026-11-04 08:00 | 2026-11-05 18:00
|  |  |  | Air Blow |  |  | 2026-11-05 18:00 | 2026-11-05 22:00
|  |  |  | เชื่อมซ่อม Z3901 A,B,C ให้จบก่อนถึงจะปิด T3902,Z3902 A,B,C |  |  | 2026-11-06 08:00 | 2026-11-07 22:00
|  |  |  | After Clean inspection [ OPE] Inspect แล้วทำการปิดทีล่ะตัวไล่จากด้านบนลงล่าง |  |  | 2026-11-06 08:00 | 2026-11-06 10:00
|  |  |  | Install Line Pipe Outlet T3902 A,B,C |  |  | 2026-11-06 10:00 | 2026-11-06 12:00
|  |  |  | Close Top Cover Z3901A,B,C |  |  | 2026-11-06 13:00 | 2026-11-06 16:00
|  |  |  | Install Line Outlet Z3901A,B,C |  |  | 2026-11-06 16:00 | 2026-11-06 22:00
ME-CM-0001 | ศุภชัย |  |  | TA26_NDT-เชื่อมซ่อม Z-3901A Dec25(RL<1.) > HW-I |  |  | 2026-11-06 08:00 | 2026-11-07 22:00
ME-CM-0002 | ศุภชัย |  |  | TA26_NDT-เชื่อมซ่อม Z-3901B Dec25(RL<1.) > HW-I |  |  | 2026-11-06 08:00 | 2026-11-07 22:00
ME-CM-0003 | ศุภชัย |  |  | TA26_NDT-เชื่อมซ่อม Z-3901C Dec25(RL<1.) > HW-I |  |  | 2026-11-06 08:00 | 2026-11-07 22:00
ME-CL-0091 | ศุภชัย |  |  | TA26_E-3808 : PM 6Y Cleaning plate & Change Rubber Gasket |  |  | 2026-11-02 09:00 | 2026-11-25 23:00
ME-CL-0092 | ศุภชัย |  |  | TA26_E-7808 : PM 6Y Cleaning plate & Change Rubber Gasket |  |  | 2026-11-02 09:00 | 2026-11-25 23:00
ME-CL-0093 | ศุภชัย |  |  | TA26_E-3804A : PM 3Y Cleaning plate & Change Rubber Gasket |  |  | 2026-11-03 09:00 | 2026-11-25 23:00
ME-CL-0094 | ศุภชัย |  |  | TA26_E-3804B : PM 3Y Cleaning plate & Change Rubber Gasket |  |  | 2026-11-03 09:00 | 2026-11-25 23:00
ME-CL-0095 | ศุภชัย |  |  | TA26_E-7804A : PM 3Y Cleaning plate & Change Rubber Gasket (Spare สั่งซื้ออยู่ที่ System Corp แล้ว) |  |  | 2026-11-03 09:00 | 2026-11-25 23:00
ME-CL-0096 | ศุภชัย |  |  | TA26_E-7804B : PM 3Y Cleaning plate & Change Rubber Gasket |  |  | 2026-11-03 09:00 | 2026-11-25 23:00
ME-CL-0083 |  |  | รอคุยพี่วี | TA26_E-3208A : PM 6Y Cleanning plate & Change Rubber Gasket |  |  | 2026-11-09 09:00 | 2026-11-19 23:00
ME-CL-0084 |  |  | เรื่องวันเข้างาน | TA26_E-3208B : PM 6Y Cleanning plate & Change Rubber Gasket |  |  | 2026-11-09 09:00 | 2026-11-19 23:00
ME-CL-0085 |  |  | ว่าขยับได้รึเปล่า | TA26_E-3208C : PM 6Y Cleanning plate & Change Rubber Gasket |  |  | 2026-11-09 09:00 | 2026-11-19 23:00
ME-CL-0086 |  |  |  | TA26_E-3209 : PM 6Y Cleanning plate & Change Rubber Gasket |  |  | 2026-11-09 09:00 | 2026-11-19 23:00
ME-CL-0087 |  |  |  | TA26_E-3411 : PM 6Y Cleanning plate & Change Rubber Gasket |  |  | 2026-11-10 09:00 | 2026-11-23 23:00
ME-CL-0088 |  |  |  | TA26_E-3502A : PM 6Y Cleanning plate & Change Rubber Gasket |  |  | 2026-11-11 09:00 | 2026-11-22 23:00
ME-CL-0089 |  |  |  | TA26_E-3502B : PM 6Y Cleanning plate & Change Rubber Gasket |  |  | 2026-11-11 09:00 | 2026-11-22 23:00
ME-CL-0090 |  |  |  | TA26_E-3605 : PM 6Y Cleanning plate & Change Rubber Gasket |  |  | 2026-11-11 09:00 | 2026-11-25 23:00
ME-CL-0083 |  |  |  | TA26_E-3208A : PM 6Y Cleanning plate & Change Rubber Gasket (Spare สั่งซื้ออยู่ที่ System Corp แล้ว)
ME-CL-0091 |  |  |  | TA26_E-3808 : PM 6Y Cleaning plate & Change Rubber Gasket (Spare สั่งซื้ออยู่ที่ System Corp แล้ว)
ME-CL-0092 |  |  |  | TA26_E-7808 : PM 6Y Cleaning plate & Change Rubber Gasket (Spare สั่งซื้ออยู่ที่ System Corp แล้ว)
ME-CL-0093 |  |  |  | TA26_E-3804A : PM 3Y Cleaning plate & Change Rubber Gasket (Spare สั่งซื้ออยู่ที่ System Corp แล้ว)
ME-CL-0094 |  |  |  | TA26_E-3804B : PM 3Y Cleaning plate & Change Rubber Gasket (Spare สั่งซื้ออยู่ที่ System Corp แล้ว)
ME-CL-0095 |  |  |  | TA26_E-7804A : PM 3Y Cleaning plate & Change Rubber Gasket (Spare สั่งซื้ออยู่ที่ System Corp แล้ว)
ME-CL-0096 |  |  |  | TA26_E-7804B : PM 3Y Cleaning plate & Change Rubber Gasket (Spare สั่งซื้ออยู่ที่ System Corp แล้ว)
|  | 800 | TK-3806 | TA26_TK-3806 : Water jet Cleaning & Inspec Vent Line 3" > TK-3806
Disassembly Vent Line 3"
Open MH TK-3806
Set Up For HPWJ
HPWJ Clening Line 3' > TK-3806
After Clean inspection
Close MH TK-3806
Install Vent Line 3"
|  | 800 | TK-3804 | TA26_TK-3804 : Water jet Cleaning & Inspec TK-3804
Disassembly Line
Open MH TK-3804
Set Up For HPWJ
HPWJ Clening TK-3804
After Clean inspection
Close MH TK-3804
Install Line
|  | 800 | F-3822 | TA26_F-3822 : Water jet Cleaning & Inspec F-3822
ถอด Flex inlet/outlet F-3822
ถอด Flange Line VG
Set Up For HPWJ
HPWJ Clening F-3822 and line > A-3813
After Clean inspection
Install Line VG
Install Flex line inlet/outlet F-3822
|  | 800 | A-3813 | TA26_A-3813 : Water jet Cleaning & Inspec A-3813
ถอด Flex inlet/outlet A-3813
Set Up For HPWJ
HPWJ Clening A-3813 and line > W-3804
After Clean inspection
Install Flex line inlet/outlet A-3813
|  | 800 | W-3804 | TA26_W-3804 : Water jet Cleaning & Inspec W-3804
ถอด Flex inlet/outlet W-3804
Set Up For HPWJ
HPWJ Clening W-3804 and line > F-3822
After Clean inspection
Install Flex line inlet/outlet W-3804
|  | 800 | F-3822 | TA26_F-3822 : Water jet Cleaning & Inspec F-3822
ถอด Flex line ชั้น 3
|  | 800 | Z-3803 | TA26_Z-3803 : Water jet Cleaning & Inspec Z-3803
ถอด Flex inlet/outlet Z-3803
ถอด SC line , SSB line
Open All Cover (ห้ามใช้ Air Impact Wrench หรือ บล็อคลม เนื่องจากเสี่ยง Nut Seed)
Set Up For HPWJ
HPWJ Clening Z-3803 and line > S-3803
After clean inspection
Install SC line , SSB line
Install Flex line inlet/outlet Z-3803
|  | 800 | S-3803 | TA26_S-3803 : Water jet Cleaning & Inspec S-3803
ถอด Flex inlet/outlet C-3803-1 ( 2 จุด )
Set Up For HPWJ
HPWJ Clening S-3803 and line discharge suction > S-3805
After clean inspection
Install Flex inlet/outlet C-3803-1
|  | 800 | M-3804 | TA26_M-3804 : Water jet Cleaning & Inspec M-3804
Disassembly All Flex line
Open MH M-3804
Set Up For HPWJ
HPWJ Clening M-3804
After Clean inspection
Close MH M-3804
Install All Flex Line
|  | 800 | TK-3801 | Disassembly Flex Line
After Clean inspection
Install Flex Line
|  | 800 | D-3819 | TA26_D-3819 : Water jet Cleaning & Inspec D-3819
Disassembly line
Set Up For HPWJ
HPWJ Clening M-3804
After Clean inspection
Install All Line
|  | 800 | D-3814 | TA26_D-3814 : Water jet Cleaning & Inspec D-3814
Disassembly Valve 4"
Open MH D-3814
Set Up For HPWJ
HPWJ Clening D-3814 > Line
After Clean inspection
Close MH D-3814
Install All Flex Line
|  | 800 | TK-7806 | TA26_TK-7806 : Water jet Cleaning & Inspec Vent Line 3" > TK-7806
Disassembly Vent Line 3"
Open MH TK-7806
Set Up For HPWJ
HPWJ Clening Line 3' > TK-7806
After Clean inspection
Close MH TK-7806
Install Vent Line 3"
|  | 800 | TK-7804 | TA26_TK-7804 : Water jet Cleaning & Inspec TK-7804
Disassembly Line
Open MH TK-7804
Set Up For HPWJ
HPWJ Clening TK-7804
After Clean inspection
Close MH TK-7804
Install Line
|  | 800 | F-7822 | TA26_F-7822 : Water jet Cleaning & Inspec F-7822
ถอด Flex inlet/outlet F-7822
ถอด Flange Line VG
Set Up For HPWJ
HPWJ Clening F-7822 and line > A-7813
After Clean inspection
Install Line VG
Install Flex line inlet/outlet F-7822
|  | 800 | A-7813 | TA26_A-7813 : Water jet Cleaning & Inspec A-7813
ถอด Flex inlet/outlet A-7813
Set Up For HPWJ
HPWJ Clening A-7813 and line > W-7804
After Clean inspection
Install Flex line inlet/outlet A-7813
|  | 800 | W-7804 | TA26_W-7804 : Water jet Cleaning & Inspec W-7804
ถอด Flex inlet/outlet W-7804
Set Up For HPWJ
HPWJ Clening W-7804 and line > F-7822
After Clean inspection
Install Flex line inlet/outlet W-7804
|  | 800 | F-7822 | TA26_F-7822 : Water jet Cleaning & Inspec F-7822
ถอด Flex line ชั้น 3
|  | 800 | Z-7803 | TA26_Z-7803 : Water jet Cleaning & Inspec Z-7803
ถอด Flex inlet/outlet Z-7803
ถอด SC line , SSB line
Open All Cover (ห้ามใช้ Air Impact Wrench หรือ บล็อคลม เนื่องจากเสี่ยง Nut Seed)
Set Up For HPWJ
HPWJ Clening Z-7803 and line > S-7803
After clean inspection
Install SC line , SSB line
Install Flex line inlet/outlet Z-7803
|  | 800 | S-7803 | TA26_S-7803 : Water jet Cleaning & Inspec S-7803
ถอด Flex inlet/outlet C-7803-1 ( 2 จุด )
Set Up For HPWJ
HPWJ Clening S-7803 and line discharge suction > S-7805
After clean inspection
Install Flex inlet/outlet C-7803-1
|  | 800 | M-7804 | TA26_M-7804 : Water jet Cleaning & Inspec M-7804
Disassembly All Flex line
Open MH M-7804
Set Up For HPWJ
HPWJ Clening M-7804
After Clean inspection
Close MH M-7804
Install All Flex Line
|  | 800 | TK-7801 | Disassembly Flex Line
After Clean inspection
Install Flex Line
|  | 800 | D-7819 | TA26_D-7819 : Water jet Cleaning & Inspec D-7819
Disassembly line
Set Up For HPWJ
HPWJ Clening M-7804
After Clean inspection
Install All Line
|  | 800 | D-7814 | TA26_D-7814 : Water jet Cleaning & Inspec D-7814
Disassembly Valve 4"
Open MH D-7814
Set Up For HPWJ
HPWJ Clening D-7814 > Line
After Clean inspection
Close MH D-7814
Install All Flex Line
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
|  | - | C7803 To S7803 | Clean line vent suct / disc exhaust fan plug + Water jet line เข้า Cyclone | 0% | 102 hrs | 2026-03-07 08:00 | 2026-03-12 20:00 | - | -
|  |  |  | Disassembly Pipe Line | 0% | 0 hrs | 2023-03-07 08:00 | 2023-03-07 08:00 | - | -
|  |  |  | Set Up For HPWJ Clening | 0% | 4 hrs | 2023-03-07 08:00 | 2023-03-07 12:00 | - | -
|  |  |  | HPWJ Clening | 0% | 1 hr | 2023-03-07 13:00 | 2023-03-07 14:00 | - | -
|  |  |  | After Clean inspection | 0% | 3 hrs | 2023-03-07 14:00 | 2023-03-07 17:00 | - | -
|  |  |  | Air Blow | 0% | 4 hrs | 2023-03-07 18:00 | 2023-03-07 22:00 | - | -
|  |  |  | Final Inspection By Bore Scope | 0% | 4 hrs | 2023-03-07 22:00 | 2023-03-08 02:00 | - | -
|  |  |  | Install Pipe Line | 0% | 28 hrs | 2023-03-08 02:00 | 2023-03-09 08:00 | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
|  | 200 | D3103 | Water jet cleaning pot + line vent to ATM | 0% | 102 hrs | 2026-03-07 08:00 | 2026-03-12 20:00 | - | -
|  |  |  | Disassembly Pipe Line | 0% | 0 hrs | 2023-03-07 08:00 | 2023-03-07 08:00 | - | -
|  |  |  | Inspection [Before] | 0% | 4 hrs | 2023-03-07 08:00 | 2023-03-07 12:00 | - | -
|  |  |  | Set Up For HPWJ Clening | 0% | 5 hrs | 2023-03-07 13:00 | 2023-03-07 14:00 | - | -
|  |  |  | HPWJ Clening | 0% | 1 hr | 2023-03-07 14:00 | 2023-03-07 17:00 | - | -
|  |  |  | After Clean inspection | 0% | 1 hr | 2023-03-07 18:00 | 2023-03-07 22:00 | - | -
|  |  |  | Air Blow | 0% | 3 hrs | 2023-03-07 22:00 | 2023-03-08 02:00 | - | -
|  |  |  | Final Inspection By Bore Scope | 0% | 14 hrs | 2023-03-08 02:00 | 2023-03-09 08:00 | - | -
|  |  |  | Install Pipe Line | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
[5 empty] | 0% |  |  |  | - | -
4 |  | - | D3201 | Water jet Cleaning Line MUD #100 | 0% | 123 hrs | 2026-03-07 08:00 | 2026-03-12 20:00 | - | -
|  |  |  | Install Sacffolding and Remove Insulation ( IF) | 0% | 0 hrs | 2023-03-07 08:00 | 2023-03-07 08:00 | - | -
|  |  |  | Disassembly Pipe Line | 0% | 4 hrs | 2023-03-07 08:00 | 2023-03-07 12:00 | - | -
|  |  |  | Lifting Exchanger | 0% | 2 hrs | 2023-03-07 13:00 | 2023-03-07 14:00 | - | -
|  |  |  | Transport To Yard | 0% | 2 hrs | 2023-03-07 14:00 | 2023-03-07 17:00 | - | -
|  |  |  | Disassembly Cover | 0% | 2 hrs | 2023-03-07 18:00 | 2023-03-07 22:00 | - | -
|  |  |  | Pull Tube Bundle 250 KG. | 0% | 2 hrs | 2023-03-07 22:00 | 2023-03-08 02:00 | - | -
|  |  |  | HPWJ Clean Tube Sheet For PdM PT Inspetion | 0% | 2 hrs | 2023-03-08 02:00 | 2023-03-09 08:00 | - | -
[5 empty] | 0% | 4 hrs |  |  | - | -
[5 empty] | 0% | 2 hrs |  |  | - | -
[5 empty] | 0% | 29 hrs |  |  | - | -
[5 empty] | 0% | 29 hrs |  |  | - | -
[5 empty] | 0% | 1 hr |  |  | - | -
[5 empty] | 0% | 25 hrs |  |  | - | -
[5 empty] | 0% | 1 hr |  |  | - | -
[5 empty] | 0% | 5 hrs |  |  | - | -
[5 empty] | 0% | 2 hrs |  |  | - | -
[5 empty] | 0% | 3 hrs |  |  | - | -
[5 empty] | 0% | 3 hrs |  |  | - | -
[5 empty] | 0% | 2 hrs |  |  | - | -
[5 empty] | 0% | 8 hrs |  |  | - | -
[5 empty] | 0% | 0 hrs |  |  | - | -
5 |  | 200 | C202 | HPWJ Clean Pipe Line | 0% | 14 hrs | 2023-03-08 08:00 | 2023-03-09 | Juktupong | Juktupong | Juktupong
|  |  |  | HPWJ Clean Pipe Line 3" x 20 M | 0% | 13 hrs | 2023-03-08 08:00 | 2023-03-08 23:00 | hds | Juktupong
|  |  |  | Final Inspection | 0% | 1 hr | 2023-03-08 23:00 | 2023-03-09 | hds | Juktupong
6 |  | 200 | E215ABCD | Pigging HP Pipe | 0% | 124 hrs | 2023-03-07 08:00 | 2023-03-13 | Pongtiwa | Pongtiwa | Pongtiwa
|  |  |  | Loose Bolt By Torque | 0% | 4 hrs | 2023-03-07 08:00 | 2023-03-07 12:00 | ALPHA | Pongtiwa
|  |  |  | Disassembly HP Flange and Pipe Support | 0% | 4 hrs | 2023-03-07 13:00 | 2023-03-07 17:00 | hds | Pongtiwa
|  |  |  | Asfound Inspectoin | 0% | 1 hr | 2023-03-07 18:00 | 2023-03-07 19:00 | OPE | Pongtiwa
|  |  |  | Install Len-Ring For Pigging | 0% | 2 hrs | 2023-03-07 19:00 | 2023-03-07 21:00 | hds | Pongtiwa
|  |  |  | Pigging | 0% | 25 hrs | 2023-03-07 21:00 | 2023-03-09 | hds | Pongtiwa
|  |  |  | Surface Lapping By Power Tools | 0% | 36 hrs | 2023-03-09 08:00 | 2023-03-11 | hds | Pongtiwa
|  |  |  | Assembly Len Ring | 0% | 14 hrs | 2023-03-11 08:00 | 2023-03-12 | hds | Pongtiwa
|  |  |  | Torque Bolt | 0% | 8 hrs | 2023-03-12 08:00 | 2023-03-12 17:00 | ALPHA | Pongtiwa
|  |  |  | Assembly Bolt Support | 0% | 6 hrs | 2023-03-12 18:00 | 2023-03-13 | hds | Pongtiwa
|  |  |  | Process Leak Test | 0% | 0 hrs | 2023-03-13 | 2023-03-13 | OPE | Pongtiwa
7 |  | 200 | E216C | Pigging HP Pipe | 0% | 124 hrs | 2023-03-07 08:00 | 2023-03-13 | Pongtiwa | Pongtiwa | Pongtiwa
|  |  |  | Loose Bolt By Torque | 0% | 4 hrs | 2023-03-07 08:00 | 2023-03-07 12:00 | ALPHA | Pongtiwa
|  |  |  | Disassembly HP Flange and Pipe Support | 0% | 4 hrs | 2023-03-07 13:00 | 2023-03-07 17:00 | hds | Pongtiwa
|  |  |  | Asfound Inspectoin | 0% | 1 hr | 2023-03-07 18:00 | 2023-03-07 19:00 | OPE | Pongtiwa
|  |  |  | Install Len-Ring For Pigging | 0% | 2 hrs | 2023-03-07 19:00 | 2023-03-07 21:00 | hds | Pongtiwa
|  |  |  | Pigging | 0% | 25 hrs | 2023-03-07 21:00 | 2023-03-09 | hds | Pongtiwa
|  |  |  | Surface Lapping By Power Tools | 0% | 36 hrs | 2023-03-09 08:00 | 2023-03-11 | hds | Pongtiwa
|  |  |  | Assembly Len Ring | 0% | 14 hrs | 2023-03-11 08:00 | 2023-03-12 | hds | Pongtiwa
|  |  |  | Torque Bolt | 0% | 8 hrs | 2023-03-12 08:00 | 2023-03-12 17:00 | ALPHA | Pongtiwa
|  |  |  | Assembly Bolt Support | 0% | 6 hrs | 2023-03-12 18:00 | 2023-03-13 | hds | Pongtiwa
|  |  |  | Process Leak Test | 0% | 0 hrs | 2023-03-13 | 2023-03-13 | OPE | Pongtiwa
8 |  | 200 | R201 | HPWJ Pipe Line | 0% | 14 hrs | 2023-03-08 08:00 | 2023-03-09 | Pongtiwa | Pongtiwa | Pongtiwa
|  |  |  | HPWJ LineInlet and Out let R201 2" x 50 M | 0% | 14 hrs | 2023-03-08 08:00 | 2023-03-09 | hds | Pongtiwa
|  |  |  | HPWJ Line Out let R201 2" x 6 M | 0% | 14 hrs | 2023-03-08 08:00 | 2023-03-09 | hds | Pongtiwa
|  |  |  | Final inspection | 0% | 0 hrs | 2023-03-09 | 2023-03-09 | OPE | Pongtiwa
9 |  | 200 | R201 | HPWJ and Manual Clean Stirrer | 0% | 108 hrs | 2023-03-08 13:00 | 2023-03-13 10:00 | SUpachock | SUpachock | SUpachock
|  |  |  | Transport Stirrer Form TPE To Yard | 0% | 4 hrs | 2023-03-08 13:00 | 2023-03-08 17:00 | hds | SUpachock
|  |  |  | HPWJ and Manual Clean Stirrer | 0% | 92 hrs | 2023-03-08 18:00 | 2023-03-12 22:00 | hds | SUpachock
|  |  |  | Final Inspectoin | 0% | 2 hrs | 2023-03-12 22:00 | 2023-03-13 | OPE | SUpachock
|  |  |  | Transport Stirrer Form Yard to TPE | 0% | 2 hrs | 2023-03-13 08:00 | 2023-03-13 10:00 | hds | SUpachock
10 |  | 200 | D205 | HPWJ Clean Line Inlet | 0% | 22 hrs | 2023-03-07 10:00 | 2023-03-08 10:00 | SUpachock | SUpachock | SUpachock
|  |  |  | Transport Pipe Line Form TPE to Yard | 0% | 2 hrs | 2023-03-07 10:00 | 2023-03-07 12:00 | hds | SUpachock
|  |  |  | HPWJ Clean Pipe Line | 0% | 10 hrs | 2023-03-07 13:00 | 2023-03-08 | hds | SUpachock
|  |  |  | Final Inspection | 0% | 1 hr | 2023-03-08 08:00 | 2023-03-08 09:00 | OPE | SUpachock
|  |  |  | Transport Pipe Line Form Yard To TPE | 0% | 1 hr | 2023-03-08 09:00 | 2023-03-08 10:00 | hds | SUpachock
11 |  | 500 | E508A | Open and Close Cover | 0% | 102 hrs | 2023-03-07 08:00 | 2023-03-12 | Pongtiwa | Pongtiwa | Pongtiwa
|  |  |  | Install Sacffolding and Remove Insulation ( IF) | 0% | 0 hrs | 2023-03-07 08:00 | 2023-03-07 08:00 | RMT | Pongtiwa
|  |  |  | Disassembly Cover and Pipe Line | 0% | 11 hrs | 2023-03-07 08:00 | 2023-03-07 21:00 | hds | Pongtiwa
|  |  |  | Re-Tube | 0% | 0 hrs | 2023-03-07 21:00 | 2023-03-07 21:00 | RMT | Pongtiwa
|  |  |  | Assembly Cover and Pipe Line | 0% | 14 hrs | 2023-03-11 08:00 | 2023-03-12 | hds | Pongtiwa
|  |  |  | Process leak Test | 0% | 0 hrs | 2023-03-12 | 2023-03-12 | OPE | Pongtiwa
12 |  | 500 | E508B | Open and Close Cover | 0% | 102 hrs | 2023-03-07 08:00 | 2023-03-12 | Pongtiwa | Pongtiwa | Pongtiwa
|  |  |  | Install Sacffolding and Remove Insulation ( IF) | 0% | 0 hrs | 2023-03-07 08:00 | 2023-03-07 08:00 | RMT | Pongtiwa
|  |  |  | Disassembly Cover and Pipe Line | 0% | 11 hrs | 2023-03-07 08:00 | 2023-03-07 21:00 | hds | Pongtiwa
|  |  |  | Re-Tube | 0% | 0 hrs | 2023-03-07 21:00 | 2023-03-07 21:00 | RMT | Pongtiwa
|  |  |  | Assembly Cover and Pipe Line | 0% | 14 hrs | 2023-03-11 08:00 | 2023-03-12 | hds | Pongtiwa
|  |  |  | Process leak Test | 0% | 0 hrs | 2023-03-12 | 2023-03-12 | OPE | Pongtiwa
13 |  | 700 | E711 | Water Jet Cleaning and Tube Inspection | 0% | 123 hrs | 2023-03-07 08:00 | 2023-03-12 23:00 | SUpachock | SUpachock | SUpachock
|  |  |  | Install Sacffolding and Remove Insulation ( IF) | 0% | 0 hrs | 2023-03-07 08:00 | 2023-03-07 08:00 | RMT | SUpachock
|  |  |  | Disassembly Pipe Line | 0% | 4 hrs | 2023-03-07 08:00 | 2023-03-07 12:00 | hds | SUpachock
|  |  |  | Lifting Exchanger | 0% | 2 hrs | 2023-03-07 13:00 | 2023-03-07 15:00 | hds | SUpachock
|  |  |  | Transport To Yard | 0% | 2 hrs | 2023-03-07 15:00 | 2023-03-07 17:00 | hds | SUpachock
|  |  |  | Disassembly Cover 424 MM | 0% | 2 hrs | 2023-03-07 18:00 | 2023-03-07 20:00 | hds | SUpachock
|  |  |  | Pull Tube Bundle 250 KG. | 0% | 2 hrs | 2023-03-07 20:00 | 2023-03-07 22:00 | hds | SUpachock
|  |  |  | HPWJ Clean Tube Sheet For PdM PT Inspetion | 0% | 2 hrs | 2023-03-07 22:00 | 2023-03-08 | hds | SUpachock
|  |  |  | PdM PT Inspection | 0% | 4 hrs | 2023-03-08 08:00 | 2023-03-08 12:00 | PdM | SUpachock
|  |  |  | Set Up For HPWJ Clean | 0% | 2 hrs | 2023-03-08 13:00 | 2023-03-08 15:00 | hds | SUpachock
|  |  |  | HPWJ Clean Inside Tube 12.7x 1.2 x 1800 MM X 234 EA and Out Side Tube | 0% | 29 hrs | 2023-03-08 15:00 | 2023-03-09 23:00 | hds | SUpachock
|  |  |  | HPWJ Inside Shell 300 x 2500 MM | 0% | 29 hrs | 2023-03-08 15:00 | 2023-03-09 23:00 | hds | SUpachock
|  |  |  | After Clean inspection | 0% | 1 hr | 2023-03-10 08:00 | 2023-03-10 09:00 | OPE | SUpachock
|  |  |  | PDM Inspection Tube ECT and IRIS | 0% | 25 hrs | 2023-03-10 09:00 | 2023-03-11 12:00 | PdM | SUpachock
|  |  |  | Final Inspection | 0% | 1 hr | 2023-03-11 08:00 | 2023-03-11 09:00 | OPE | SUpachock
|  |  |  | Assembly Tube Bundle | 0% | 5 hrs | 2023-03-11 09:00 | 2023-03-11 15:00 | hds | SUpachock
|  |  |  | Hydro Test 15 KG/CM2 Shell by XX | 0% | 2 hrs | 2023-03-11 15:00 | 2023-03-11 17:00 | hds | SUpachock
|  |  |  | Hydro Test 15 KG/CM2 Tube by XX | 0% | 3 hrs | 2023-03-11 18:00 | 2023-03-11 21:00 | hds | SUpachock
|  |  |  | Assembly Cover | 0% | 3 hrs | 2023-03-12 08:00 | 2023-03-12 11:00 | hds | SUpachock
|  |  |  | Transport To LDPE Plant | 0% | 2 hrs | 2023-03-12 11:00 | 2023-03-12 14:00 | hds | SUpachock
|  |  |  | Install Exchanger | 0% | 8 hrs | 2023-03-12 14:00 | 2023-03-12 23:00 | hds | SUpachock
|  |  |  | Processleak Test | 0% | 0 hrs | 2023-03-12 23:00 | 2023-03-12 23:00 | OPE | SUpachock
14 |  | 500 | X505 | Water Jet Clean Tube | 0% | 22 hrs | 2023-03-06 08:00 | 2023-03-07 08:00 | Juktupong | Juktupong | Juktupong
|  |  |  | Disassembly Cover | 0% | 5 hrs | 2023-03-06 08:00 | 2023-03-06 14:00 | hds | Juktupong
|  |  |  | Asfound Inspectoin | 0% | 1 hr | 2023-03-06 14:00 | 2023-03-06 15:00 | hds | Juktupong
|  |  |  | Demon HPWJ Tube 14 x 9000 MM 5 EA | 0% | 16 hrs | 2023-03-06 15:00 | 2023-03-07 08:00 | hds | Juktupong
15 |  | 700 | XXV782,783,HCV916 | HPWJ Clean Matal Trap 7 EA and Cone Strainer 4 EA | 0% | 112 hrs | 2023-03-08 08:00 | 2023-03-13 10:00 | Juktupong | Juktupong | Juktupong
|  |  |  | Transport Form TPE To Yard | 0% | 4 hrs | 2023-03-08 08:00 | 2023-03-08 12:00 | KC | Juktupong
|  |  |  | HPWJ and Manual Clean | 0% | 29 hrs | 2023-03-08 13:00 | 2023-03-09 21:00 | KC | Juktupong
|  |  |  | Final Inspectoin | 0% | 3 hrs | 2023-03-09 21:00 | 2023-03-10 | OPE | Juktupong
|  |  |  | Transport Form Yard to TPE | 0% | 2 hrs | 2023-03-13 08:00 | 2023-03-13 10:00 | KC | Juktupong
16 |  | 200 | F216 | Cleaning F216 | 0% | 36 hrs | 2023-03-08 08:00 | 2023-03-10 | Juktupong | Juktupong | Juktupong
|  |  |  | Disassembly Cover Jacket | 0% | 0 hrs | 2023-03-08 08:00 | 2023-03-08 08:00 | RMT | Juktupong
|  |  |  | Asfound Inspection | 0% | 1 hr | 2023-03-09 08:00 | 2023-03-09 09:00 | OPE | Juktupong
|  |  |  | HPWJ Clean Filter | 0% | 9 hrs | 2023-03-09 09:00 | 2023-03-09 20:00 | hds | Juktupong
|  |  |  | Air Blow | 0% | 2 hrs | 2023-03-09 20:00 | 2023-03-09 22:00 | hds | Juktupong
|  |  |  | Final Inspection | 0% | 2 hrs | 2023-03-09 22:00 | 2023-03-10 | OPE | Juktupong
|  |  |  | Assembly All | 0% | 0 hrs | 2023-03-10 | 2023-03-10 | RMT | Juktupong
17 |  | 200 | E236B | Clean and Inspection | 0% | 54 hrs | 2023-03-10 08:00 | 2023-03-12 20:00 | Thikamporn | Thikamporn | Thikamporn
|  |  |  | Disassembly Pipeline and Cover | 0% | 6 hrs | 2023-03-10 08:00 | 2023-03-10 15:00 | hds | Thikamporn
|  |  |  | Asfound Inspection | 0% | 2 hrs | 2023-03-10 15:00 | 2023-03-10 17:00 | OPE | Thikamporn
|  |  |  | HPWJ Clean Exchanger Pressure about 100 Bar | 0% | 28 hrs | 2023-03-10 18:00 | 2023-03-12 | hds | Thikamporn
|  |  |  | Final Inspection | 0% | 2 hrs | 2023-03-12 08:00 | 2023-03-12 10:00 | OPE | Thikamporn
|  |  |  | Assembly All Part | 0% | 8 hrs | 2023-03-12 10:00 | 2023-03-12 20:00 | hds | Thikamporn
|  |  |  | Leak Test | 0% | 0 hrs | 2023-03-12 20:00 | 2023-03-12 20:00 | OPE | Thikamporn
19 |  | 200 | E261 | Clean and Inspection | 0% | 54 hrs | 2023-03-10 08:00 | 2023-03-12 20:00 | Thikamporn | Thikamporn | Thikamporn
|  |  |  | Disassembly Pipeline and Cover | 0% | 6 hrs | 2023-03-10 08:00 | 2023-03-10 15:00 | hds | Thikamporn
|  |  |  | Asfound Inspection | 0% | 2 hrs | 2023-03-10 15:00 | 2023-03-10 17:00 | OPE | Thikamporn
|  |  |  | HPWJ Clean Exchanger Pressure about 100 Bar | 0% | 28 hrs | 2023-03-10 18:00 | 2023-03-12 | hds | Thikamporn
|  |  |  | Final Inspection | 0% | 2 hrs | 2023-03-12 08:00 | 2023-03-12 10:00 | OPE | Thikamporn
|  |  |  | Assembly All Part | 0% | 8 hrs | 2023-03-12 10:00 | 2023-03-12 20:00 | hds | Thikamporn
|  |  |  | Leak Test | 0% | 0 hrs | 2023-03-12 20:00 | 2023-03-12 20:00 | OPE | Thikamporn
19 |  | PCS | PCS2 | Inspect Line transfer PCS2 ท่อนตรง 1 ท่อน | 0% | 53 hrs | 2023-03-10 08:00 | 2023-03-12 19:00 | Thikamporn | Thikamporn | Thikamporn
|  |  |  | Install Scaffolding ( If) | 0% | 0 hrs | 2023-03-10 08:00 | 2023-03-10 08:00 | RMT | Thikamporn
|  |  |  | Disassembly Pipe Line | 0% | 10 hrs | 2023-03-10 08:00 | 2023-03-10 20:00 | hds | Thikamporn
|  |  |  | Asfound Inspection | 0% | 2 hrs | 2023-03-10 20:00 | 2023-03-10 22:00 | OPE | Thikamporn
|  |  |  | Cleaning Pipeline (if) | 0% | 10 hrs | 2023-03-11 08:00 | 2023-03-11 20:00 | hds | Thikamporn
|  |  |  | Final Inspection | 0% | 2 hrs | 2023-03-11 20:00 | 2023-03-11 22:00 | OPE | Thikamporn
|  |  |  | Assembly Pipe Line | 0% | 9 hrs | 2023-03-12 08:00 | 2023-03-12 19:00 | hds | Thikamporn
|  |  |  | Leak Test | 0% | 0 hrs | 2023-03-12 19:00 | 2023-03-12 19:00 | OPE | Thikamporn